Agata/AMBMin/Oct07/final

Minutes AGATA Management Board

Next Meeting: 25th October 2007 start 9:00 finish 17:00. University of Cologne.

Present:

D. Bazzacco

A. Gadea

G. Duchêne

J. Nyberg

P. Reiter

J. Simpson 			Project Manager and Secretary

Ch. Theisen

W.Korten			ASC representative

1. Apologies for absence

None

2. Minutes of the last meeting16-17th July GSI.

The draft minutes Agata/AMBMin/Jul07/02D were accepted as a correct record of the meeting.

Will distributed as Agata/AMBMin/Jul07/final.

3. Matters arising from the last meeting and actions outstanding from last phone conference

The final technical report on AGATA was discussed. This document is stated as a requirement of the MoU and as part of the EURONS project.

Action JS to initiate preparation by the AMB of the AGATA technical report (end of 2008). Need to check on MoU requirements (current and future).

Action PR: Report on the first triple module is required (for EURONS) by end of this year.

### Action: Web page discussion JN could be responsible with help from students. Saclay are offering a person to contribute to the web design? Both options seem good so will discuss at next phone conference or when WK, JN and JG are together.

Ongoing

Actions on the AMB from the ASC meeting:

- AMB to formalise responsibilities for the above and to provide a planning for the commissioning experiments.

Action on JN and AG to prepare a plan, see below.

- AMB to contact A. Korichi to sort out how this is to be done, in agreement with the EU tendering regulations.

Done.

- AMB to investigate needs and costs for data storage beyond the budgeted 100 Tb.

- An evaluation of the required human resources will be made by the AMB, W.K. and J.S

- Running cost analysis

Action all: To consider what effort will be available, resources and tasks that each country and laboratory will contribute to the AGATA 1(.

Initial feedback to be reported at the next AMB.

Ongoing.

Action all, in addition to comments above any extra information or “real costs” to be sent to WK.

Ongoing

Effort requirements still required.

Action All: All information by 23rd November (Capital and effort for the new MoU to 2012).

HV controller units: New layout being designed at Saclay with connector mounted.

Action all. Check what has been ordered from CTT (re HV).

Italy has checked and its contract says:

…The cryostat will be equipped with three high voltage supplies (ISEG MHx 50 103 2 2.5), supply via D Sub 15 housing mounted plugs, or with high voltage filters and standard SHV plugs. (remark 3) …

Remark 3: Still to be settled is the HV supply of the AGATA experiment. CTT suggested and thereby quotes to equip the cryostats with individual ISEG HV modules mounted directly to the cryostat housing. As an alternative CTT accepts to equip the cryostat with HV filters and standard SHV plugs for the same price.

Italy: ISEG is explicitly written but is it ISEG/SHV plugs?.....

Germany similar

UK: HV supplies included.

Sweden/Turkey Plugs or modules provided by customer.

Possibility of recording on tapes?

Action: CT to investigate if tape backup is feasible. Cost of drives etc.

Done see DAQ report.

Grid? Need a virtual AGATA organisation for test.

Action: JN to investigate in detail what is possible and what’s involved.

See DA report.

Action DB to produce a list of required electronics.

Remove until decision for an in-beam test is taken.

Action: JN to co-ordinate the simulation and which reactions could be used.

Remove until decision for an in-beam test is taken.

Action: All to consider the detailed commissioning experiments at the next AMB.

Paper to be prepared by AG and JN. To be circulated to the AMB prior to the AGATA week.

The plan will be presented at the next AGATA week.

Ongoing.

4. ASC report

Next meeting 4th December in Cologne.

FP7 status. AGATA bid was not successful. Funds will be integrated into host laboratories access budget. Hopefully this will be additional funding. Allocation to AGATA has to be agreed with host laboratories.

An MoU/agreement between AGATA and each host laboratory will be agreed. Timescales for this are to have the MoU with Legnaro in place by early 2008 and an MoU for Ganil in place by early 2009. These MoUs will specify what the host laboratory and the wider AGATA collaboration provides. Operation costs must be provided by the collaboration starting at the latest in 2009.

The new MoU is being prepared. It is expected that this new MoU will commence on 1/1/2008. It is possible that the majority of the stakeholders will have signed this MoU by spring 2008 but this will be discussed again at the ASC. This date takes into account the financial and decision making process in each country.

5. Funding status and capital allocation

Action: All to check GD proposed redistribution of finances.

Check latest version of capital file, GD and all to look for latest and circulate.

Next iteration could possibly swap funds in Sweden for DAQ to DA?

TUM has ~15k euro. What could this money be used for?

GD to discuss with S.Gales how Amel/ IPNO could proceed to obtain the funds for pre-processing.

6. Reports from Working Groups

- Detector module and characterisation

Report from PR is attached.

The AMB agreed that if the fixes of the microphonics do not work then the detectors should be rejected.

Saclay will pay for the replacement dewar on their test cryostat (vacuum leak).

C001 in Munich cryostat or C003 in Liverpool cryostat will be sent to Liverpool for scanning ASAP after the faults given in the report are fixed.

Questions again regarding the cost of triple cryostats!

Synchronisation of GRT4 clocks is an issue? Discuss at AGATA week.

GSI scanning system. Overestimation of data rate. Have some data which is to be compared with Liverpool data. More details needed which will be reported at the AGATA week.

Orsay scanning system. The present setup works with the GABRIELA digital electronics which is used for ~2 months periods in Dubna. Upgrade foreseen for a fixed digital electronics.

Orsay is ready to get a detector by Feb 2008.

Detector group needs a new team leader.

Candidate Bart Bruyneel (Cologne post doc).

This was agreed.

Action PR to inform Bart.

b. Front end processing

From DB’s presentation.

Digitization

- Prototype delivered to LNL at the beginning of August

  - to define final parameters (gain, bandwidth)

  - tested but no real work done

- Construction of 18 units proceeding well

  - Modules being tested

  - Boards will need to be modified

    - for final gain parameters and Nyquist filter

    - for correct handling of ToT

    - for new core preamplifier with two ranges

  - One order still in discussion (Turkey)

Possibility of buying the 3 digitizers in the UK.

Status of Turkey to be ascertained. Turkey could the funds be used for something else

Action JS

Pre-processing

- New ATCA Carrier

  - 3 PCBs available ( 2 prototype mounted

  - hardware tests ~80 % ready (

    - DPRAM soldered with an offset in one of them

  - revised version

    - November/December: new routing (CERN) and PCB production

    - January/February: population and tests

- New segments Mezzanine

  - 3 prototypes mounted

  - hardware tests ~completed

  - no revision foreseen

- New Core Mezzanine

  - ready for PCB production

  - awaiting results of integration tests

- New GTS Mezzanine

  - on hold

- Integration tests of Carrier+3 Segment mezzanines + 1 GTS (1st version)

  - ongoing at Padova  (22-31 October)

    - Ch.Oziol (IPNO) + B.Travers and X.Lafay (CSNSM)+ Padova Team + I.Lazarus (few days)

  - testing optical fibers input (MGTs in loopback)

  - readout to carrier DPRAM

The AMB wishes to congratulate the effort so far in the production of the new hardware.

- Production HW (assuming integration tests successful)

  - Carrier

  - ready for production according to plan (mid March 2008)

  - production (36+ boards) to be managed by IPNO

    - Enough know how? (idea is to have the 3rd PCB tested by Ch.Oziol+ in Padova)

    - enough manpower?

    - Boundary scan to ease testing (RAL)

    - Test and validation ~1 week/board/person

    - Availability of funds?

DB will discuss IPNO effort etc. with J.Pouthas.

New engineer (3rd) will start in Orsay.

  - Segment Mezzanine

  - ready for production according to plan (end March 2008)

  - production (~108+ boards)

    - Test and validation  x-days/board/person

    - Availability of funds?

  - Core Mezzanine: 	present plan is beginning of July 2008?

  - GTS: 		present plan is begin February 2008 ( not realistic

Need to decide what are the long delivery time items that are safe to order and attempt to place orders for long delivery items as soon as possible.

- Production VHDL for Carrier

  - is the critical issue ( typically ~70 % of the effort

  - integration of code estimated to take 8 month to a skilled person

  - discussions on how to proceed:

    - IPNO alone (as planned) or Padova still involved

    - choice of RTOS for the FPGA (VxWorks or Linux) depend on who does the work

    - main issue is the availability of man power to develop the VHDL

Need a proposed solution and confirmation or not from I Lazarus. Ideally need a clear path by the AGATA  week, but at the latest for the next ASC meeting

- Implementation of processing algorithms (Segment and Core Mezzanine.)

  - IHPC code implemented in segment mezzanine as a black-box

  - Plans to develop the Strasbourg code using a GTS mezzanine

    - Base Line restorer

    - Time over threshold

- Readout of carrier

  - PCI Express (RAL)

    - Got the core through Europractice

  - FASTER (LPC Caen)

    - ALTERA version OK

    - Xilinx porting: synthesis OK; needs to be tested on real hardware

  - PCI Express memory mapped (limited to ~30 MB/s)

- Phased delivery of hardware and firmware

Global Clock and trigger

- GTS Mezzanine Version  1

  - OK, being used for testing the ATCA CARRIER

- GTS Mezzanine Version  2

  - Prototype ready since one year

  - Tests on hold awaiting end of ATCA carrier development

- Global trigger processor

  - First version based on GTS mezzanines on a VME carrier (ready)

  - Firmware developed in SystemC

  - Automatic (almost) translation to VHDL

  - Synthesized and running on a test board

- Timely completion of work problematic

Pulse Shape Analysis

- PSA algorithms validation

  - Cologne experiment (2005)

  - Liverpool scan-table data

  - Imaging

  - New data

  - New experiment  (only if major delay)

- Dependency on calculated signal basis is critical

- Narval implementation split in 3 blocks

  - Readout and local event builder

  - Preprocessing of data (calibrations,..)

    - This is probably the most complicated part because we have to make in real time what took ~1 year for the Cologne experiment

  - PSA: first implemented algorithm likely to be a Grid Search

- Need to finish the development of the AGATA Data Format (ADF) to inject proper data into the PSA

- Discussion on the needed hardware

c) Data Acquisition

The presentation by C Theisen was distributed by email prior to the meeting and is added to these minutes.

* Hardware

We found an agreement on the CPUs i.e. only new pizza boxes, Xeon.

Two option for the disks: Fiber Channel or DAS. Better performances with FC but more expensive.

Agreed to proceed to spend these funds with 5-6 pizza boxes and FC disks

Action: CT to organize orders with Ganil, Lyon and V Pucknell.

* Teams status

Orsay will visit Legnaro end of October to glue the Run Control + Narval + GUI

Hope to have a demo during the AGATA week.

d) Ancillary detectors and ancillary detector integration

Progress in the AGAVA firmware, problems found with the EXOGAM readout (VXI) in addition to the known GTS-AGAVA communication errors. New test programmed for the AGATA week ~12th to 16th November.

n.3 AGAVA modules for 9 k€ ordered by INFN-LNL to be delivered next year after prototype acceptance.

Design of the new PRISMA front-end readout hardware/software ongoing

Multiplicity Filter (Helena) as possible ancillary for the experimentation phase at LNL under evaluation.

e) Design and Infrastructure

From report of PR an email from John Strachan:

Mechanics meeting at IKP, Cologne

A meeting related to the mechanics of the AGATA frame and the assembly of the AGATA triple detectors in the Legnaro frame and the final spectrometer mechanical frame was initiated by John Strachan. Participants: John Strachan, Rob Griffiths   STFC, Tobias Engert   GSI, Bart Bruyneel, Juergen Eberth, Herbert Hess, Peter Reiter   IKP, Cologne University, Heinz-Georg   Thomas  CTT

John Strachan distributed the following mail concerning the outcome of the meeting:

1. survey report. http://www.eng.dl.ac.uk/secure/np-work/Survey/2007_09_13_cologne

1.1 The report showed that the faces of the endcap distorted significantly under

vacuum. This distortion is into the detector, and so is not cause the endcaps to collide,

but may be an issue for other reasons. Heinz-Georg has independently carried out some checks using DTIs (Dial Test Indicators), and also so some distortion. Heinz-Georg suggested glueing some stiffening rings around the inside of the endcap to reduce distortion if required.

At the cologne meeting we discussed:

1.2 The report showed that the mechanical construction of the detector was not good enough to achieve a sphere as required. Therefore an adjustment system will have to be designed and made. This was agreed by all.

2.  A proposed detector adjustment frame was shown at the meeting, which involves a fixture

to locate the detector in its correct position and some adjustment for mounting. This design was accepted in principle and a prototype should be detailed and manufactured. (I will send an edrawing file on Monday. Some concern was raised as to the weight of the detector (80kg with adjustment rings), and so manual handling of the detector needs to considered.

3.    Table top support frame - for use when maintaining the detector. The design shown at the

meeting was accepted with minor changes and should be detailed and manufactured.

4.      HV boxes - no problems with space constraints.

There are some photos at the link also, I hope this helps.

Regards

John

Adjustment mechanics has become expensive.

What is the cost?

Action: JS will ask John Strachan for status.

Done. Cost to be discussed and action plan at next AMB.

Cost for adjustment is £4k per detector.

Need 1 gauge £5k

Setup for flange adjustment £4k

So for 6 detectors of the demonstrator £33k.

Also needed

Support stand £5k.

Lifting arrangement approx since not yet designed £10k

Grand total for demonstrator ~£50k (~75k euro).

The UK will cover these costs.

Not including the cost of ISEG modules the cost of the HV units will be 3k euro per crystal.

Action JS to organise sending the flange to LNL.

- LV modules have been ordered. Prototype to be delivered mid-Dec 07

- HV box:  problems encountered at Saclay with this modules. Main problem is reliability and no current monitor nor current limitation possible. This is to be checked by GSI.

The Team has a VC tomorrow and will discuss the different ways to follow.

The document ISEG HV Module: problems and solutions, was distributed by G Duchene prior to the meeting.

- PLC and GUI: communications problems between GSI and Saclay. In addition, funding problems at GSI has lead to the GSI representation by J. Gerl at the last sitting meeting of the Team in Finland.

Saclay pays the travel for T. Habermann for a ~2 days stay at Saclay for a PLC-PC communication test with the right material and for a deep exchange about the GUI. Date not yet fixed but should be late Oct. or early Nov.

The document ISEG HV Module: problems and solutions, was distributed by G Duchene prior to the meeting.

Options were discussed. Tests are ongoing in GSI, should be done 3rd week of November.

Possibility of starting with standard SHV plugs and standard HV.

Low voltage module prototype ready mid Dec 2007. Want to do test of this with triple cluster and with one unit of the digitizer mid Jan 2008. If successful start production in Feb 2008.

Three first HV prototypes in March 2008.

Need to perform a test of HV boxes on a triple cluster in March 2008.

If a backup solution is required need to know where the equipment (HV) is. CAEN crate available in LNL but only negative polarity of the available HV cards are available. Does Köln have positive polarity HV cards ? Possibility to get HV modules from the spare parts of EUROBALL ?

Cabling of demonstrator: not all details clear right now; solutions to be found during installation. LNL working on this topic. LNL-GANIL meeting to be organised when a layout will be fixed.

Items that follow demonstrator to GANIL to be decided  later on. Agreement between the three host- labs to be discussed and agreed.

f) Gamma-ray tracking, simulations and data analysis

GRID

  - AGATA Virtual Organization

    - Waiting for certificate, which is needed for submission of VO application. Certificate obtained 25/10!

    - Approval of VO application should be fast

  - Already existing AGATA GRID resources:

    - Orsay:		Tier2,	4 CPUs, 3 TB

    - Lyon:		Tier3,	20 CPUs, 10 TB + 5 TB

    - Uppsala:	Tierx (distr), 2 CPUs, 3 TB

  - Need to start testing the GRID as soon as VO approved

  - LNL (G. Maron) may host AGATA grid resources up to  ~200 TB + necessary CPUs

AD data analysis funding: 20 k€

  - French funds which must be spent latest end of Nov 2007 otherwise lost.

  - Proposal of spending by O. Stezowski, Ch. Theisen et al. (discussed at recent French AGATA meeting and briefly with JN):

    - Buy the minimum needed for LNL:

    - 1 pizza box with ~2 TB of disks + at least 4 GB of RAM and few cores

    - 1 or 2 cheap PCs for display

    - Use remaining funds for the grid

Note: we do not have enough funding for offline storage and analysis

Discussed that this is not urgent and should not be spent yet.

Therefore, agreed that Lyon should purchase more DAQ storage. Expenditure on online analysis to be later when, for example GRID requirements are known.

Detector Database

The architecture of the detector database was presented.

Need to decide which database to use: CMS tracker database is proposed.

GD requests that each AMB member checks the architecture part in relation with its W Gr and comment as soon as possible.

AGATA week presentations

  - Simulations:

    - Enrico Farnea: Status report on simulations

    - Grzegorz Jaworski: Simulations of ancillary devices: RFD, EXOGAM, DIAMANT

    - Olivier Stezowski: Simulations of EXOGAM and AGATA

    - Olivier's student(?): Simulations of EUROBALL and AGATA

  - Tracking:

    - Araceli Lopez-Martens: Status report on tracking

    - Stanislav Tashenov: Tracking of partially absorbed events

    - Francois Didierjean: The deterministic annealing method

  - Data bases and GRID:

    - Karl Hauschild: Status report on data bases

    - Gilbert Dûchêne or Karl Hauschild: Report from infra-structure team concerning  the detector parameter database

    - Johan Nyberg: The AGATA GRID Virtual Organisation

  - Data analysis:

    - Olivier Stezowski: Status report on data analysis

    - Olivier Stezowski: Short summary of AGATA Dataflow Library

    - Enrico Farnea: Implementation of a C++ version of the PRISMA ion tracking program

    - Jurek Grebosz: The RISING data analysis package

g) EURONS

See ASC report

7. Commissioning of the demonstrator at LNL and project plan

Mechanics

-Final machining of the flanges waiting for the test with the prototype to be sent from

Daresbury.

-Prototype expected end October week, start machining mid November

-Evaluated high conductivity surface treatment (Alocrom/Alodine) for the flanges to be

tested with the prototype mid November

-Pre-machined parts for the structure arrived to LNL start of welding expected beginning

December

-Design of the Legnaro LN2 support structure by 2nd November.

-Reaction chamber machining ongoing, expected ready by December/January.

-Design of the new beam-line ready under evaluation at Daresbury

Cryogenics

-Design LN2 distributor, collector and evacuation line production waiting the ok from LNL after checking the clearance.

-Test of LN2 detector pipes to produce a design condensation-free

-Ready the procurement of material to build the cabling for the cryogenic system (valve PT100 and  valve power supply)

Electronic Infrastructure

-Procurement of the flexible cable tray ongoing

-Design of the Digitizers racks (47U) ongoing

-Modification of existing racks to hold the pre-processing ongoing

Ge Detector lab

-Space for the AGATA Ge detector Lab. Available and installation of the basic

infrastructures ongoing.

-Procurement of the Siemens PLC for the LVPS and HV control ongoing

-Procurement of two AGATA LVPS from AXIS ongoing

DAQ/Ancillaries

-Work being done on Narval installation and ancillary detectors front-end

Documentation

-LNL Document server available

Data Analysis

-PRISMA new version sorting software under development

Installation  costs of the AGATA Demonstrator at LNL

Mechanical Infrastructures:

•N.2 prototypes and n.15 AGATA flanges

•Support structure for 15 AGATA flanges at PRISMA

•New reaction chamber

•Support structure for the cryogenic elements

Beam Line:

•N.1 vacuum pump for beam-line

•New telescopic beam-line

•Video-camera for beam-line

Cryogenic infrastructures

•Liquid nitrogen distribution and collector manifolds, flexible line and evaporator

•Cabling infrastructures for cryogenic valves and valve PT100

•LV 24V 50Hz power supply for the cryogenic valves

•LN2 pipes

Cabling and infrastructure for the electronics and DAQ

•Modification and Installation of racks for pre-processing

•Cable guide and modification of the cable tray for PRISMA

•N.2 Digitizer Racks (47U)

•TR2-Racks for the DAQ at LNL

Ge Detector laboratory

•Cryogenic infrastructure

•Vacuum oven

•PLC control

•N.2 AXIS AGATA low voltage power supply modules

•Workstation for test bench DAQ

•Electronics for test bench DAQ

•Vacuum gauges

Electronics Laboratory

•Basic instrumentation

•ATCA crate

•Switch for crate ATCA

Total investment through INFN-AGATA project: 175k€

Investments on LNL infrastructures excluded

Core AGATA investments excluded

Open questions:

-Detector adjustment system ( recently design, production costs, see item 6(e).

-Flange assembly tools ( under evaluation,

8. Next in-beam test

Not discussed

9. Next AGATA week

Any information to AG regarding parallel sessions, team meetings etc.

JS to ask J Strachan to organise a mechanical meeting. Contact AG for invitees.

10. Ge production

Not discussed

11. AOB

No time

12. Date and location of next meeting and dates of phone conferences.

18/1/2008 Paris G. Duchene to organise a room.

Phone conferences /VRVS

19/11/2007 14:00 CET

6/12/2007 10:15 CET

18/12/2007 10:15 CET

8/1/2007 10:15 CET

| Detector | delivery | owner | status CAT |
| --- | --- | --- | --- |
| A001 | 11/05 | GANIL | rejected |
| B001 | 11/05 | Padova | rejected |
| C001 | 12/05 | Padova | accepted |
| A002 | 04/06 | Munich | rejected |
| A001* | 06/06 | GANIL | accepted |
| C002 | 07/06 | GANIL | accepted |
| B002 | 08/06 | GANIL | accepted |
| A003 | 11/06 | Liverpool | rejected |
| C003 | 03/07 | Liverpool | accepted, microphonics within specs |
| B003 | 06/07 | Liverpool | accepted, microphonics within specs |
| B001 | 06/07 | Padova | CAT done, microphonics, details see text |
| A002 | 06/07 | Munich | CAT done, microphonics, details see text |
| C004 | 09/07 | Ankara | CAT done, microphonics, details see text |
| A004 | 09/07 | Ankara | Mounted in test cryostat |
| A003 | 10/07 | Liverpool |  |

AGATA detector and characterisation working group

Informal report to AMB members

P. Reiter, October 25, 2007

Summary of detector deliveries and status of Customer Acceptance Tests CAT

Latest detector deliveries since AMB meeting

- detector C004 owned by University of  Ankara delivered and tested

- detector A004 owned by University of  Ankara is delivered to Cologne

- repaired detector A003 owned by University of  Liverpool is delivered to Cologne

Status of CAT at Cologne

- At the moment detector A004 is mounted for the CAT. Detector A003 was delivered October 10th.

- Reports on C003 and B003 are not sent out to owners. These detectors show microphonic behaviour but the measurement results stay within the specifications. At the moment we intend to include them into the list of detectors, which may need a rework.

- Reports on B001, A002 and C004 are negative, all three detectors failed the CAT, because core measurements could not performed due to massive microphonic behaviour of the detectors.

Acceptance test of the asymmetric AGATA capsules

B001-74034  and A002-74030

The test of both capsules were performed including two AGATA test cryostats: first the standard Cologne test cryostat equipped with HeKo preamplifiers and second the Munich test cryostat equipped with GANIL preamplifiers and the AGATA core preamplifier.

Detector B001 (owner INFN Legnaro)

1. Detector B001 in Munich test cryostat, 03.08.2007

- all segment contacts short-connected to ground of cold capsule

- core energy resolution values for 60Co energies (1.1 and 1.3 MeV)

at 3500 V : 2.94/3.05 keV

4000 V : 3.05/3.15 keV

4500 V : 4.50/4.60 keV

- very microphonic, amplitude approx. 4 V, amplitude increases with HV

- also warm preamplifiers removed -> no change in microphonics, core energy resolution values: 3.60/3.70 keV

- detector upside down (Ge crystal up): no change in microphonics, core energy resolution values 4.13/4.34 keV

- detector in horizontal position: no change in microphonics, core energy resolution values: 4.60/4.70 keV

Conclusion: segments are not causing microphonics

2. Detector S002 in Munich test cryostat, 13.08.2007

- all segments short-connected

- noise band after main amplifier approx. 15 mV

- core energy resolution value: 2.21 keV

Conclusion: Munich test cryostat is not suffering from microphonics with symmetric detector S002

3. Detector B001 in Munich test cryostat, 17.08.2007

- all segments short-connected

- core resolution at 3000 V 2.82/2.79 keV

4000 V 2.28/2.39 keV

4500 V 2.15/2.25 keV (absolute silence in the lab)

4500 V 2.30/2.40 keV (normal noise level, like speaking in the lab)

- microphonics with oscillation frequency of 500 Hz, typically 1000 - 1200 Hz

- measurements were repeated, 20.08.2007

- core energy resolution at 4500 V 2.5/2.6 keV

- noise band 20 mV after main amplifier

- crystal is very microphonic, typical oscillation amplitude of main amplifier signal of approx. 4 V

Conclusion: microphonics of B001 persists in Munich test cryostat, standard operation not possible, core energy resolution not within specifications.

Detector A002 (owner TU München)

1. Detector A002 into Cologne test cryostat, 23.08.2007

- Detector was mounted in cryostat for standard customer acceptance test with segment preamplifiers connected

- high voltage applied up to 2000 V

- very strong microphonics

- spontaneous oscillation with approx 2 V amplitude

- core energy resolution measurement not feasible

2. Detector S002 into Cologne test cryostat, 28.08.2007

- noise band after main amplifier approx. 15 mV

- noise band after preamplifier approx. 5 mV

- core resolution in different positions:

- vertical position  (Ge crystal down)

energy resolution values:  2.12/2.23 keV

- horizontal position

energy resolution values: 2.15/2.22 keV

- vertical pos (Ge crystal up)   2.14/2.22 keV

- in all three positions no microphonics, no spontaneous oscillations

3. Detector A002 in Munich test cryostat, 29.08.2007

- all segments short-connected

- noise band after main amplifier approx. 25 mV

- noise band after preamplifiers approx. 15 mV

- core energy resolution values in different positions:

- - vertical position (Ge crystal down):     2.54/2.63 keV

- - vertical position (Ge crystal up):          2.41/2.49 keV

- - horizontal position:                              2.64/2.76 keV

- in all three position spontaneous oscillations

4. Detector S002 in Munich test cryostat, 13.08.2007

- all segments short-connected

- Noise band after main amplifier approx. 15 mV

- core energy resolution: 2.21 keV

Conclusion: microphonics of A002 persists in Cologne and Munich test cryostat, both cryostats were cross checked with detector S002, standard operation of A002 not possible, core energy resolution not within specifications.

Detector C004 (owner University of Ankara)

C004 shows similar behaviour like A002 and B001, no core energy measurement possible

Ankara group joined acceptance test

- 10.10.07 detector C004 mounted in Cologne test cryostat

- high voltage fixed with a clamp on capsule

- detector cooled down on 15.10., vacuum at 5*10^-6

- 16.10 PT100 = 29.4 Ohm

- 4 segments missing

- core noise band without HV, after main amplifier, 150 mV,

no spontaneous oscillation

- at 200 V core shows very microphonic, amplitude of spontaneous oscillation (main amp) > 1V

- at 1000 V microphonics gets worse, no core energy resolution measurement possible

- 18.10 powered up to 500 V, same microphonics, visit of  Mrs. Loche from manufacturer Canberra is informed on Cologne site

- detector warmed up, no measurements could be performed

Detector A004 (owner University of Ankara)

Detector A004 mounted in Cologne test cryostat 23.10.

- high voltage fixed with a clamp on capsule

- the high voltage feedthrough on capsule is glued (kitted) from Canberra

- all segment contacts short-connected to ground of cold capsule

Phone conference IKP and Canberra

The results of the CAT of detectors B001 and A002 were informally reported and discussed first with Canberra in order to localize potential reasons for the microphonic behaviour of B001 and A002. The intention is also to find out a possibly more general problem of the AGATA crystals with respect to microphonics. A first phone conference with participation from Canberra (Lampert, Loche, Quirion) and IKP (Bruyneel, Eberth, Hess) was held September 17.

First steps:

- to glue the high voltage feedthrough of one capsule B001 or A002 to help to exclude one of the possible source of microphony.  Canberra is preparing the glue and a procedure to use it.

- Cologne people will join the next factory acceptance test at Lingolsheim. Canberra people claim they never observe this problem. It seems useful to examine the differences in mounting in the Canberra test bench and the AGATA test cryostats.

Status of detector C001 and cryostat at IKP

The Saclay result related to the vacuum of the test cryostat with C001 was confirmed at IKP, Cologne. After pumping down to 1.8*10-5 mbar over a weekend cooling with LN2 was started. The vacuum improved one order of magnitude down to 2 * 10-6 mbar and jumped all of sudden back to values in the 10-5 mbar region. A leak check with He inside the dewar with a small straw tube clearly showed a massive leak in the upper part inside the dewar above the LN2 level. The vacuum is now worse than before.

The dewar needs to be exchanged. According to Heinz-Georg Thomas the cryostat was ordered by Saclay. We have to figure out finances for replacement of the dewar and reassembly.

Detector C001 is mounted in Munich test cryostat. First tests could reproduce the old energy resolution values of the core within the specification limits. First tests of the segments were also successful and within the energy specs. Microphonics remains a problem, but much less pronounced than before at Saclay.

Details of Detector C001 – Cryostat TUM:

- Vacuum improved from 8*10^-6 to 3*10^-6 during cooling with LN2

- At 3 kV high voltage core resolution @ 1.17/1.3 MeV: 2.69/2.81 keV

3.5 kV:  core @ 1.17/1.3 MeV: 2.43/2.59 keV

4 kV:  core @ 1.17/1.3 MeV: 2.33/2.35 keV

4.5 kV: core @ 1.17/1.3 MeV: 2.25/2.33

Segments @ 1.17/1.3 MeV:

D1: 2.31/2.33 keV

E3: 2.01/2.09 keV

F2: 1.98/2.02 keV

A4: 1.94/2.05 keV

B5: 2.05/2.14 keV

C6: 2.10/2.24 keV

F6: 2.04/2.14 keV

- Segment F4 was missing due to a broken wire in the cold part which was fixed after warming up the detector

Core @ 122 keV: 1.38 keV

Segments @ 59.5 keV:

A1: 1.2 keV

B1: 1.19 keV

C3: 1.09 keV

B2: 1.06 keV

D4: 1.1 keV

E5: 1.07 keV

F6: 0.99 keV

- After fixing the broken wire the cryostat was cooled down again (04.10).

Core and all segment signals present

High frequency oscillation on core and segments (100 MHz frequency; >20 mV amplitude on the preamp signal). Oscillation couldn’t be removed in the cooled state. The PT100 is assumed to be responsible for the oscillation.

Status detector C003 – Cryostat UK

Core resolution @1.3 MeV: 2.5 keV (digital acquisition)

Crosstalk on Segment C1 needs to be solved

Crosstalk moved in latest measurement to segment D1.

Asymmetric AGATA Triple Cryostat

Status of assembly (done by H.-G. Thomas, CTT)

- mechanics of three ATCs (SN10034, 10035, 10036) delivered to IKP University Cologne (after vacuum and cooling tests and mechanic dummy mounting at CTT)

- Electronics prepared for three ATCs (cold preamps, vacuum cabling, feedthroughs, motherboard,MDR etc.)

- Sn10034: equipped with complete electronics, compatibility tests with test pulser electronics performed successfully

- SN10034: mounting of one detector together with two elect. dummies

- SN10034: pumping for cool down

Future of characterisation and scanning

provide in a short and informal way the following information:

- What is the status of the scanning tables at Liverpool, Orsay and GSI?

What are the limitations in operation at Liverpool (scanning time for smallPET, man power) Orsay (available electronics, DAQ system and offline sorting?), GSI (hardware of fibre or scintillators, proof of principle, rate limitations).

- How many detectors may be scanned at your laboratory per year?

- Is a routine scanning operation envisaged and maintained in the next years?

- Are there obvious short comings of equipment/manpower and necessities for future funding requests in order to operate the scanning tables efficiently?

Reply by Andy Boston; Liverpool.

Regarding Liverpool, the scanning table is now available. We have recently commissioned a second system which we use for our CZT/Silicon work. Within the next 12 months, the large (AGATA) table is available with no restriction, as is the GRT DAQ. We have recently employed new PDRAs (shared with other detector projects) and have significant PhD student manpower available. Matt Dimmock is completing his PhD thesis on the characterisation of the AGATA symmetric detectors. We now have Carl Unsworth (a new PhD student), who will be working on the asymmetric detectors along with our PDRAs. We have planned to do routine scanning though to the mid/late 2008 - beyond this if necessary.

Our SmartPET Lytech DAQ is in final commissioning - which should mean we can run this entirely separately from the GRT4 DAQ from end 2007. This system has the potential to be used in the future for scanning if necessary.

Our coincidence scans take 2 months to complete with 1 month preparation time (including singles scanning). Over twelve months this realistically means we can do 3 detectors (allowing for shipping/downtime etc). We don't anticipate any new spend, providing the Loanpool BGO detectors remain available.

In the UK, the Universities of Surrey and Manchester are presently commissioning detector scanning systems. These systems could be used should there be a requirement once analysis of the initial asymmetric data has allowed us the judge what the future scale of any scanning operation needs to be. Indeed we need to answer the questions very quickly; (1) What will be done if it is found extensive scanning of future detectors is required (2) How best to optimise the pulse shape databases between detector shapes & indeed detectors of the same shape if required.

Reply by Amel Korichi; Orsay.

Regarding our scanning system this is the status:

We have been using TNT2 cards for the electronics but as I told you this electronics belong to GABRIELA and is now being used by many other collaborators which make the task difficult.

I have requested funds to equip our system with its own electronics and if we get this from IN2P3 we will have a much more flexibility for the AGATA scanning detectors. In addition, now the DAQ system is fully operational using NARVAL and the commissioning was performed with an EXOGAM detector this summer. My student is doing the analysis for a complete single scan (2 days measurement) with traces collection.

Also since the detector had to move back to GANIL, we could only perform a coincidence measurement using a standard Ge detector coupled to 3 TOHR modules as again the electronics had to move again to Stasbourg and we only had 1 card (4 channels) The data analysis is under way by my student and also a routine scanning method has to be carried out by my student for her PhD.

Now concerning the question of how many detectors can be scanned in Orsay, the answer will be given later according to the requested additional equipments (electronics) also as we discussed last year at the AGATA week, if we will have to scan a triple cluster as suggested by Eberth then the answer is "zero" as our table has been designed for a single crystal.

No reply from GSI

DAQ overheads provided by CT